Coral Lookout

60-Day Plan to Earn $100,000

Day-by-day operating planner · Starts from an existing warm lead: Prof. Courtney (Puerto Rico)

Honest framing: $100K in 60 days is aggressive for a student-driven product. This plan does not assume 2,000 schools at $49/mo. It assumes a small number of high-value closes (university / NGO / CSR / prepaid school clusters) unlocked by the Puerto Rico relationship, plus relentless outbound. Treat $100K as the stretch target; use the weekly checkpoints to know if you are on track.

1. Revenue math (what must close)

Target mix (adjust to real conversations — totals ≈ $100K cash collected or contract-signed + invoiceable within 60 days):

Puerto Rico university / lab partnership (annual): $15,000–$25,000

2–3 Research & NGO annual licenses: $15,000–$30,000 each → $30,000–$60,000

1 CSR / brand ocean sponsor (challenge + map visibility): $15,000–$25,000

School cluster / district prepaid annuals (founding rate ~$500–$1,000/school × 15–40 schools): $15,000–$30,000

Optional: education/climate micro-grant or accelerator prize: $5,000–$15,000

Rule: Prefer annual prepaid invoices over monthly $49 churn. Sell outcomes (classroom program, verified PR reef dataset, grant-ready reports), not “an AI scanner.”

2. Warm lead: Prof. Courtney (Puerto Rico)

You already have a positive email thread. That is your unfair advantage for Days 1–14. Do not let it go cold.

Reply within 24 hours with a clear ask: 20-minute call + demo + how Coral Lookout helps her students / research

Offer a Puerto Rico pilot: free or discounted for her class + co-branded “Caribbean Reef Watch” chapter

Ask for intros: other professors, aquarium contacts, local NGOs, NOAA / DNER contacts, student leaders

Propose a deliverable in 30 days: N student scans geotagged in PR waters + shared research dashboard

Path to paid: convert pilot → departmental license or multi-course annual partnership

ACTION: Paste the actual email reply into a “Lead notes” section at the end of this doc and update Day 1–3 tasks to match her exact wording (interest in teaching vs research vs both).

3. Weekly scoreboard (non-negotiable)

Week 1: Courtney call booked + 20 new qualified emails sent + live demo URL polished

Week 2: Pilot agreement outline signed (even if $0) + 5 intros requested + first school invoices drafted

Week 3: First paid commitment ($5K+) OR 10 school annuals reserved

Week 4: Pipeline ≥ $150K face value (needed to close $100K)

Week 5: At least $40K signed or invoiced

Week 6: At least $70K signed or invoiced

Week 7: Collect cash / purchase orders; expand PR network

Week 8: Hit $100K signed+cash OR document shortfall + next 30-day close list

If Week 3 has $0 committed, cut vanity product work and double outreach hours.

4. Day-by-day planner (Days 1–60)

WEEK 1 — Activate Puerto Rico + sales machine

Day 1 — Reply to Prof. Courtney + lock the narrative

Send a thoughtful reply referencing her email points; propose 2–3 call times this week

Attach or link a 2-minute Loom of /scanner → /map → /class

Create a one-page Google Doc: “Puerto Rico Pilot — Coral Lookout” (goals, student workflow, what you need from her)

Set up a simple CRM sheet: Lead | Org | Type | $ Potential | Stage | Next step | Date

Revenue focus: Warm lead → pilot path

Day 2 — Offer design for Courtney

Define Pilot A (classroom only): free 60 days, then $2,500–$5,000 departmental annual

Define Pilot B (research + class): includes data export + co-authorship acknowledgment → $10K–$25K annual

List 5 questions for the call (students/semester, field trips, data needs, colleagues, budget cycle)

Prepare screen-share demo script (8 minutes max)

Revenue focus: Price the PR offer before the call

Day 3 — Asset pack for outreach

Export /vision and /business into a short PDF one-pager for partners

Write 3 email templates: Teacher, University researcher, NGO program lead

Confirm production site URL, Stripe school checkout, and a working teacher demo account

Add “Puerto Rico / Caribbean” framing to partner inquiry talking points

Revenue focus: Tools ready to sell

Day 4 — Courtney call (or chase)

Hold the call; take notes; confirm next milestone (date for student onboarding)

If no reply yet: polite bump + alternate times + offer async Loom Q&A

Ask for 3 introductions before the call ends

Send same-day thank-you with written summary + proposed pilot MoU outline

Revenue focus: Convert interest → calendar commitment

Day 5 — Build the $100K pipeline list

Add 40 targets: Caribbean universities, aquariums, reef NGOs, US coastal school districts, ocean brands

Prioritize anyone Courtney named

Tag each with estimated deal size and why they’d pay

Schedule 10 outbound emails for Day 6

Revenue focus: Pipeline construction

Day 6 — First outbound blast

Send 10 personalized emails (not mass spam) using templates

Post in 2 teacher / marine-education communities with soft CTA

Message 5 schools that already care about climate curriculum

Log every reply in CRM

Revenue focus: Start top-of-funnel

Day 7 — Week 1 review

Scoreboard check: call held? demo ready? CRM live?

Rewrite weak email template based on replies

Block Week 2 calendar: 2 hrs outreach + 2 hrs product daily

Rest, but schedule Monday Courtney follow-through first thing

Revenue focus: On-track if Courtney is advancing

WEEK 2 — Pilot paperwork + intros

Day 8 — Pilot MoU draft

Send 1–2 page MoU: scope, free period, success metrics (#scans, #students), path to paid license

Include logo usage + optional co-branded gallery collection for Puerto Rico

Ask Courtney who signs on university side

Revenue focus: Paper → future invoice

Day 9 — Onboard her students (soft launch)

Create School Chapter for her course; send join code + 1-page student guide

Offer a 15-minute live onboarding for the class (or recorded)

Collect first 10 student scans if possible

Revenue focus: Usage creates switching cost

Day 10 — Ask for intros (scripted)

Send Courtney a short forwardable blurb + ask for 5 intros

Also ask: aquarium educators, NOAA affiliates, local dive shops with education programs

Add every intro to CRM within 1 hour of receipt

Revenue focus: Network effects start here

Day 11 — Teacher / school outreach day

Email 15 teachers/schools with founding annual pricing ($399–$588/year prepaid)

Offer “Caribbean cohort” discount if they join with PR pilot

Book 3 demos for Week 3

Revenue focus: School ARR base

Day 12 — NGO / research outreach day

Email 10 NGOs/labs with Research & NGO one-pager ($15K–$30K annual)

Lead with verified observations + classroom workforce + Puerto Rico foothold

Offer discovery calls, not feature tours

Revenue focus: High-ticket pipeline

Day 13 — Sponsor shortlist

List 15 ocean / outdoor / education brands for CSR challenge sponsorship

Draft sponsor package: $15K / $25K / $40K tiers (challenge, map badge, report mention)

Send 5 sponsor emails

Revenue focus: Non-school revenue

Day 14 — Week 2 review + money forecast

Update CRM probabilities; forecast expected value

If Courtney stalled: call/text pathway via student leader or department admin

Prepare invoices template (Stripe or PDF)

Revenue focus: Need visible path to first $10K

WEEK 3 — First dollars

Day 15 — Close first paid school(s)

Follow up every warm teacher demo with a 48-hour founding-rate deadline

Offer annual prepaid only for the sprint (simplifies cash)

Aim: 5–10 schools committed

Revenue focus: Cash + social proof

Day 16 — Courtney paid path conversation

Share early pilot metrics (students joined, scans, map pins)

Present departmental license options with clear deliverables

Ask what budget line / grant could fund Year 1

Revenue focus: Convert pilot → paid

Day 17 — Demo marathon

Run as many demos as possible (stack 30-minute slots)

Always end with: price, start date, who signs

Send proposals same day

Revenue focus: Velocity

Day 18 — Proposal factory

Standardize 3 proposal PDFs: School Annual, University Lab, NGO License

Include /vision pillars relevant to each buyer

Send to all open opportunities

Revenue focus: Professional close assets

Day 19 — Grant / prize applications

Submit 1–2 fast education/climate opportunities if deadlines fit

Use Paradigm / hackathon story + PR pilot as proof

Track expected decision dates inside 60-day window

Revenue focus: Upside cash

Day 20 — Sponsor follow-ups

Call or LinkedIn-message brand contacts

Offer a time-bound “Caribbean Student Reef Challenge” for Q next month

Revenue focus: CSR path

Day 21 — Week 3 checkpoint — hard

Must have either (a) ≥$5K signed/invoiced OR (b) signed LoI with payment date inside 30 days

If neither: pause non-essential coding; 6 hours/day outreach for Week 4

Publish a short public update: “Puerto Rico pilot live” (with Courtney permission)

Revenue focus: Kill vanity work if revenue is zero

WEEK 4 — Expand Caribbean + US school clusters

Day 22 — Cluster sell: “10 schools for $X”

Pitch district STEM coordinators: 10-school pack at discounted annual

Use PR pilot as geographic story for Caribbean / coastal districts

Revenue focus: Bigger ACV

Day 23 — University expansion beyond Courtney

Email 20 marine science / education faculty (US + Caribbean)

Mention active PR collaboration (accurate wording only)

Revenue focus: Repeatable university motion

Day 24 — NGO second wave

Follow up all Week 2 NGO emails

Add restoration NGOs that need monitoring reports

Revenue focus: Report product sells here

Day 25 — Negotiate first large deal

Focus calendar on the largest open opportunity

Ask for budget confirmation and procurement steps

Offer phased payment (50% now / 50% Day 45) if needed to book revenue

Revenue focus: Protect the $100K path

Day 26 — Case study draft

Write 1-page PR pilot case study (problem, workflow, early results)

Get Courtney quote approval

Revenue focus: Sales acceleration asset

Day 27 — Invoice day

Send all ready invoices; confirm payment methods (card, ACH, PO)

Chase unpaid soft commits

Revenue focus: Cash collection starts

Day 28 — Week 4 review

Pipeline face value should be ≥ $150K to have a shot at $100K closed

Re-rank top 10 deals; drop low-probability noise

Revenue focus: Focus

WEEK 5 — Close hard

Day 29 — Top-10 deal calling day

Call every hot lead; no email-only

Ask for decision date this week

Revenue focus: Direct closes

Day 30 — Procurement help

Offer W-9 / vendor packet / student data privacy one-pager

Remove buyer friction

Revenue focus: Unblock finance

Day 31 — School pack close

Push district/school pack to signature

Add onboarding dates so they feel momentum

Revenue focus: ARR batch

Day 32 — University license close

Finalize Courtney or other university paperwork

Invoice immediately upon signature

Revenue focus: High-ticket

Day 33 — NGO license close

Trade scope for speed: Year-1 data access + 2 reports + training

Revenue focus: Don’t overbuild before paid

Day 34 — Sponsor decision

Get yes/no on CSR package; if no, move to next brand

Revenue focus: Avoid limbo

Day 35 — Week 5 checkpoint

Target ≥ $40K signed or cash-in

If behind: cut price only for annual prepaid closes this week (founding rates)

Revenue focus: Measure ruthlessly

WEEK 6 — Push to $70K+

Day 36 — Second university / lab

Use PR case study to close similar Caribbean/US lab

Ask Courtney for one more intro

Revenue focus: Repeatable motion

Day 37 — Teacher webinar

Host 30-min public teacher webinar; end with founding annual CTA

Record for async selling

Revenue focus: One-to-many sales

Day 38 — Follow-up blitz

Touch every open deal twice today (AM email / PM call)

Revenue focus: Volume

Day 39 — Expand school chapters

Convert webinar attendees to paid annuals

Offer buddy-school referral credit

Revenue focus: Compound schools

Day 40 — Grant status chase

If applied, request status; prepare backup plan if delayed past Day 60

Revenue focus: Don’t count hope

Day 41 — Collections

Chase all outstanding invoices; escalate politely

Revenue focus: Cash ≠ signature

Day 42 — Week 6 checkpoint

Target ≥ $70K signed/cash

Identify exact gap to $100K and which 2 deals fill it

Revenue focus: Gap math

WEEK 7 — Fill the gap

Day 43 — Gap-deal focus

Work only the 2–3 deals that can hit $100K

Ignore vanity metrics

Revenue focus: Focus

Day 44 — Upsell existing pilots

Expand scope: multi-course, multi-campus, data API add-on

Revenue focus: Expand ACV

Day 45 — Emergency outbound

20 new high-fit emails to orgs that can decide fast

Revenue focus: New oxygen

Day 46 — Partner co-sell

Ask Courtney/NGO champions to join a close call

Social proof closes finance

Revenue focus: Champion selling

Day 47 — Legal / signature day

Clear all redlines; DocuSign everything pending

Revenue focus: Paperwork

Day 48 — Payment processing

Confirm wires/cards landed; screenshot CRM cash total

Revenue focus: Truth of cash

Day 49 — Week 7 review

Publish internal cash vs signed vs promised

Prepare final 11-day sprint plan

Revenue focus: Transparency

WEEK 8 — Finish line

Day 50 — Final close calls

Every remaining deal gets a same-day decision ask

Revenue focus: Close

Day 51 — Founding rate sunset

Last chance founding pricing expires tonight

Create urgency without lying

Revenue focus: Deadline

Day 52 — Collect & onboard

Cash collection + white-glove onboarding for paid accounts

Revenue focus: Retention starts now

Day 53 — PR public story

With permission: announce Puerto Rico partnership milestones

Use for remaining closes

Revenue focus: PR leverage

Day 54 — Clean CRM

Mark lost deals with reasons; keep nurture list for Day 61+

Revenue focus: Learning

Day 55 — Stretch upside

One more sponsor or school pack attempt if under $100K

Revenue focus: Last swing

Day 56 — Ops hardening

Ensure paid customers have support channel + success checklist

Revenue focus: Don’t churn Day 61

Day 57 — Financial reconciliation

Sum cash received + irrevocable POs that finance can count

Separate “verbal yes”

Revenue focus: Honest total

Day 58 — If short of $100K

List exact remaining gap and 14-day recovery plan

Do not fake metrics on the website

Revenue focus: Integrity

Day 59 — Retrospective

What messaging closed? What wasted time?

Update offer pricing for next quarter

Revenue focus: Systemize

Day 60 — Declare result + next 60

Write final scoreboard

Set next target (e.g., $250K pipeline) using network effects from PR + schools

Revenue focus: Compound

5. Daily timebox (repeat every weekday)

90 min — Outreach / follow-ups / calls

60 min — Product work that unblocks sales (see companion implementation doc)

30 min — CRM update + scoreboard

30 min — Courtney / warm-lead nurturing until paid

Weekends: lighter — collections, content, and scheduling only unless a deal is hot.

6. Lead notes — Prof. Courtney (fill in)

Paste key lines from her email here so the plan stays accurate:

Date of email: _______________

What she liked / offered: _______________

Teaching vs research interest: _______________

Constraints (IRB, semester timing, budget): _______________

Introductions she can make: _______________

Agreed next step + date: _______________

7. Success definition

Count toward $100K only: cash received, or signed contract + invoice with payment terms inside 60 days that a real buyer acknowledges. Do not count page views, free signups, or verbal enthusiasm.