Coral Lookout

60-Day Website Implementation Plan

Everything to build/improve on the site during the revenue sprint — sequenced to help close Puerto Rico, schools, NGOs, and sponsors.

Principle: Ship only what increases trust, conversion, retention, or data-moat credibility. Defer Digital Twin / predictive fleet robotics until paid demand exists.

1. Goals of the build plan

Make pilots effortless (join codes, teacher UX, Puerto Rico cohort)

Make buyers trust the product (honest AI, provenance, exports, case studies)

Make money flow (Stripe reliability, proposals, partner pages)

Advance the data moat (verified scans, gallery quality, research exports)

Support Prof. Courtney’s classroom/research workflow first

2. Priority tiers

P0 — Must ship to sell this week

P1 — Needed to close university/NGO deals

P2 — Strengthens moat / Phase 2–3 story

P3 — Vision pillars that wait for revenue (digital twin, full predictive AI, public API platform)

3. Day-by-day implementation planner

WEEK 1 — Sales-ready foundation (P0)

Day 1 — Production reliability

Confirm production deploy (Vercel) with env vars for Supabase + Stripe

Fix any broken /pitch redirect; ensure /vision and /business load

Add uptime check on /api/health

Verify drag-drop scanner works on production (files + web image drops)

Day 2 — Puerto Rico pilot mode

Add optional cohort/tag for scans & chapters: region = Puerto Rico / Caribbean

Teacher dashboard: show cohort name + join instructions printable page

Create /pilot or section on /class with “Student quick start”

Day 3 — Demo & partner polish

Polish /vision CTAs and ensure mobile layout

Add “Book a pilot” mailto or form on /business and /vision

Ensure /founder and contact paths are obvious

Day 4 — Auth & chapter friction removal

Simplify login → join chapter → first scan happy path

Empty states with clear next actions on /teacher, /class, /gallery

Fix any School Demo Mode confusion for real paid teachers

Day 5 — Honest AI trust panel

On /scanner results: clear label of what the model does / doesn’t claim

Show pipeline steps + confidence in buyer-friendly language

Link to methodology blurb (short /research or /vision subsection)

Day 6 — Onboarding emails / copy

In-app checklist for teachers: create chapter → invite → first assignment

Student checklist: join → scan → pin → gallery

Puerto Rico-specific welcome copy if cohort flag set

Day 7 — Week 1 QA

End-to-end test as Teacher and Student on production

File bugs; ship hotfixes only

WEEK 2 — Classroom & provenance (P0/P1)

Day 8 — Assignment workflow

Teacher can create a simple assignment (“Scan a reef image + pin location”)

Student completion status on roster

Day 9 — Exports teachers need

Improve CSV export: student, scans, scores, dates, lat/lng

One-click “Class summary PDF” (even basic print stylesheet)

Day 10 — Verified observation fields

Require/encourage GPS, timestamp, contributor display name on save

Store validation score / pipeline model version on scan records

Show provenance on gallery post detail

Day 11 — Image rights & safety

Keep image-rights confirmation; add report/flag on gallery

Basic moderation queue stub for teachers/admins

Day 12 — Map filters for partners

Filter map by school chapter / Puerto Rico cohort / date range

Shareable map link for Courtney’s class

Day 13 — Case study page scaffold

Add /case-studies or section with Puerto Rico pilot placeholder

Pull live counts (students, scans) when available

Day 14 — Week 2 QA + demo script update

Record new Loom reflecting Week 1–2 features

WEEK 3 — Conversion & billing (P0/P1)

Day 15 — Stripe hardening

Test School Chapter checkout end-to-end on production

Add annual prepaid price option (critical for $100K sprint)

Clear success/cancel pages with next steps

Day 16 — Pricing page clarity

Update /business: founding annual school price, university/NGO custom CTA

Add FAQ: procurement, student privacy, what pilot includes

Day 17 — Partner inquiry CRM-lite

Improve /community?partner=inquiry form → email + stored lead fields

Auto-reply with calendar link / one-pager

Day 18 — Proposal-ready PDF export

Generate simple partner one-pager from /vision content (print CSS or PDF lib)

Day 19 — School landing improvements

Dedicated /schools page: benefits, demo screenshots, CTA to /teacher

Testimonials placeholder (Courtney quote when approved)

Day 20 — Performance & SEO basics

Metadata for /vision, /business, /schools, /scanner

OG images for sharing with professors

Day 21 — Week 3 regression test

Billing + chapter + scanner + gallery full pass

WEEK 4 — Research-grade credibility (P1)

Day 22 — Research export pack

Export scans as CSV/GeoJSON for researchers

Include confidence, model version, lat/lng, timestamps

Day 23 — Benchmark views (lightweight)

On /research: compare chapter or region summary stats vs global demo sites

No need for full ML yet — honest descriptive analytics

Day 24 — Report generator v1

One-click “Class / Pilot Report” PDF: counts, map snapshot link, top scans

Template language suitable for grant appendices

Day 25 — Gallery quality controls

Better compression, required captions for class posts

Filter gallery by verified / class / region

Day 26 — AI improvement (practical)

Improve reef validation robustness; document limitations

Prepare hook for stronger health model without breaking UI pipeline

Day 27 — Admin visibility

Simple admin metrics: scans/day, active chapters, funnel

Day 28 — Week 4 QA

Have a non-founder teacher test the full flow; fix friction

WEEK 5 — Collaboration & trust (P1/P2)

Day 29 — Multi-teacher chapter support

Allow co-teachers / TAs on a chapter if not already

Day 30 — Annotation / notes on scans

Student or teacher notes field; visible in exports

Day 31 — Expert review stub

“Needs review” / “Educator verified” badge on observations

Courtney (or staff) can mark verified — feeds Verified Dataset pillar

Day 32 — Privacy & compliance page

Public /privacy and student-data summary for school procurement

Day 33 — NGO partner workspace lite

Partner dashboard: see contributed scans, download export, brand mark

Day 34 — Accessibility pass

Keyboard/focus, contrast, alt text on key flows (scanner, teacher)

Day 35 — Week 5 stabilization

Bug bash; freeze risky refactors

WEEK 6 — Scale features that sell (P1/P2)

Day 36 — Bulk student invite

CSV roster upload improvements; invite links

Day 37 — Inter-school leaderboard opt-in

Caribbean cohort competition view for engagement stories

Day 38 — Challenge sponsorship hooks

UI slots for sponsored challenge name/logo (CSR package fulfillment)

Day 39 — API preview (private)

Document internal/partner read API for scans summary (keyed, not public yet)

Enough to show “API Platform” trajectory on sales calls

Day 40 — Mobile UX hardening

Scanner + class flows excellent on phones (field use)

Day 41 — Localization prep

Extract critical strings; optional Spanish for Puerto Rico classrooms

Day 42 — Week 6 release

Tagged production release notes for partners

WEEK 7 — Moat accelerators (P2)

Day 43 — Time-series basics

If same location scanned twice, show simple before/after on research/map

Day 44 — Species / label fields (manual + AI assist)

Optional species tags on scans; store for benchmark database

Day 45 — Government report template

Second PDF template: biodiversity / bleaching summary language

Day 46 — Dataset citation

Generate a citation snippet for class datasets (Verified Global Dataset story)

Day 47 — Webhook / Zapier-ish export

Email weekly digest to teachers with class stats

Day 48 — Security review basics

Rate-limit fetch-image and analyze endpoints; audit public routes

Day 49 — Week 7 QA

Load test analyze lightly; fix timeouts/errors users hit in demos

WEEK 8 — Polish, proof, defer list

Day 50 — Case study page go-live

Publish Puerto Rico results with approved quotes and charts

Day 51 — Marketing site polish

Homepage hero CTA tests; clearer path for Teachers vs Partners vs Students

Day 52 — Onboarding automation

Post-payment checklist emails for schools

Day 53 — Analytics

Funnel events: visit → signup → chapter join → first scan → paid

Day 54 — Documentation

Teacher guide + Student guide + Partner overview in /docs or PDFs

Day 55 — Bug freeze + hotfix only

Stabilize for demos and onboarding

Day 56 — Performance pass

Image sizes, map load, LCP on key pages

Day 57 — Accessibility + mobile final QA

Fix remaining blockers

Day 58 — Deferred backlog grooming

Explicitly park: Digital Twin 3D, drone integrations, full predictive AI, public API marketplace

Keep them on /vision as Planned with honest status

Day 59 — Release notes for customers

Summarize what shipped in 60 days for paid accounts

Day 60 — Handoff to next quarter

Prioritize roadmap from real buyer requests (not ideas)

Align next builds to closed deals’ contracts

4. Feature checklist (master backlog)

P0 — Sell this month

Production stability (auth, scanner, chapters, Stripe annual)

Teacher onboarding + printable join guide

Puerto Rico / cohort tagging + shareable map

Honest AI methodology copy

Partner inquiry form + /schools landing

Case study page

P1 — Close university / NGO

Research CSV/GeoJSON exports

Class/pilot PDF reports

Provenance fields (GPS, time, contributor, model version)

Educator-verified badge

Privacy/procurement page

Annual prepaid billing

Spanish-friendly critical UI (if PR classrooms need it)

P2 — Moat compounds

Time-series before/after

Species tags

Citation snippets

Private partner API preview

Sponsored challenges UI

Weekly teacher digests

P3 — Explicitly later (unless a signed contract requires it)

Drone / GoPro / ROV automated ingest

Full scientific disease/species models with papers

Predictive bleaching forecasting

3D digital twin

Public developer API platform

Government NOAA-format automated filing

5. Engineering rules for the sprint

No large rewrites

Every feature must map to a sales conversation or pilot pain

Prefer exports and trust over flashy new surfaces

Keep /vision status chips honest as things ship

Pair with the Revenue Plan: if Week 3 revenue is $0, cut P2 and do only P0 sales-unblockers

6. Definition of done (each week)

Deployed to production

Tested as Teacher + Student

Mentioned in demo script / Loom

Logged in CRM as a selling point if relevant